## Sheet1
Feng Xiao
Stages | Date | Content | Start | End | Hours | Comments | Additional Work
(1) Project Preparation | 5/15/2015 | Team Meeting．
| 5/18/2015 | Read project Information from E-mail links. | 10am | 6pm | 8
| 5/19/2015 | Literature Review | 10am | 6pm | 8
| 5/20/2015 | Check how to transfer AutoCad to Abaqus | 10am | 6pm | 8
| 5/21/2015 | Literature Review | 10am | 6pm | 8
| 5/22/2015 | Review WTC7 Structural Layout | 10am | 6pm | 8
(2) AutoCAD Layout | 5/25/2015 | Start to work on 1st Floor AutoCAD | 10am | 6pm | 8
| 5/26/2015 | Review AutoCAD S12-13, Case study Abaqus | 10am | 6pm | 8
| 5/27/2015 | Study on ABAQUS Pin Connection, Review AutoCAD S12-13 | 10am | 6pm | 8
| 5/28/2015 | Review AutoCAD S12-13, Classify Beam and Truss Member | 10am | 6pm | 8
| 5/29/2015 | Review AutoCAD S12-13, Classify Beam and Truss Member | 10am | 6pm | 8
| 6/01/2015 | Review AutoCAD S1 and S12-13 | 10am | 6pm | 8
| 6/02/2015 | Check AutoCAD S1, Draw and Modify S1 | 10am | 6pm | 8
| 6/03/2015 | Check AutoCAD S12-13, Draw and Modify S12-13 | 10am | 6pm | 8
| 6/04/2015 | Check and Modify AutoCAD Draw S2 | 10am | 6pm | 8
| 6/05/2015 | Check and Modify AutoCAD Draw S3 | 10am | 6pm | 8
(3) Two Story Simple Test (ABAQUS) | 6/08/2015 | Define S12-13 Frame in Abaqus (Sample) | 10am | 6pm | 8
| 6/09/2015 | Define S12-13 Deck in Abaqus (Sample), Assemble Frame and Deck | 10am | 6pm | 8
| 6/10/2015 | Define S12-13 Column (Sample), Assemble Column | 10am | 6pm | 8
| 6/11/2015 | Define S12-13 Beam, Column Connection | 10am | 6pm | 8
| 6/12/2015 | Study Beam-Deck Connection, Literature Review of Fundation | 10am | 6pm | 8
| 6/15/2015 | Define Foundation | 10am | 6pm | 8
| 6/16/2015 | Study Beam-Deck Connection | 10am | 6pm | 8
| 6/17/2015 | Define Beam-Deck Connection, Define Finite Elment. | 10am | 6pm | 8
| 6/18/2015 | Study Abaqus Load Define | 10am | 6pm | 8
| 6/19/2015 | Creat job, Correct Beam Orientation and other errors | 10am | 6pm | 8
| 6/20/2015 | Set up Camera, Study Beam Deck Connection | 10am | 6pm | 8
| 6/21/2015 | Solved Problem "a shell element must have more than one integration point to calculate bending stiffness". | 10am | 6pm | 8
Find Problem "elements have missing property definitions" is in Beam Section
| 6/22/2015 | Solved Problem "missing property definitions". | 10am | 6pm | 8
Find Problem: Not including self-weight.
(4) Simple Beam Test (ABAQUS) | 6/23/2015 | Creat Non-Composite Beam Slab, Study apply dead load in Abaqus | 10am | 6pm | 8
| 6/26/2015 | Creat Composite Beam Slab, Study Abaqus Constraints | 10am | 6pm | 8
| 6/27/2015 | Test Abaqus Constraints, Plan to Built Wire Plane and Wire Beam Connection | 2pm | 8pm | 6
| 6/29/2015 | Study Wire Plan, Wire Beam Connection | 10am | 6pm | 8
| 6/30/2015 | Verify Beam and Shell connection, Built Test Sample | 10am | 6pm | 8
| 7/1/2015 | Run Test Sample, Modify the Test Sample | 10am | 6pm | 8
| 7/2/2015 | Compare Test Sample with Hand Calculation, Plan to Refine Links between Deck and Beam | 10am | 6pm | 8
| 7/3/2015 | Added 6 Link for test sample, Compared the results. | 10am | 6pm | 8
| 7/6/2015 | Study Composite Beam Calculation | 10am | 6pm | 8
| 7/7/2015 | Hand Calculated Composite and Non Composite Simple Support Beam | 10am | 6pm | 8
| 7/8/2015 | Verify Calculated Results | 10am | 6pm | 8
| 7/9/2015 | Show the comparison between hand calculation and ABAQUS | 10am | 6pm | 8
(5) Research on WTC 7 S12 - 13 Rigid Condition (ABAQUS) | 7/10/2015 | Put Connections into Two Story Building | 10am | 6pm | 8
| 7/13/2015 | .IGES can transfer AutoCAD 3D to ABAQUS | 10am | 6pm | 8
| 7/14/2015 | Set up Plan to Built Two Floor System | 10am | 6pm | 8
| 7/152015 | Start to Built Cross Section | 10am | 6pm | 8
| 7/16/2015 | Study Cross Section Orientation, Research on Cross Section Define Methods | 10am | 6pm | 8
| 7/17/2015 | Built Floor 12-13 Beam Cross Section 1 | 10am | 6pm | 8
| 7/20/2015 | Built Floor 12-13 Beam Cross Section 2 | 10am | 6pm | 8
| 7/21/2015 | Built Floor 12-13 Beam Cross Section 3 | 10am | 6pm | 8
| 7/22/2015 | Draw Floor 12-13 Column Cross Section | 10am | 6pm | 8
| 7/23/2015 | Checked Auto CAD 3D (Floor 12-13), Transferred to ABAQUS | 10am | 6pm | 8
| 7/24/2015 | Creat Parts, Assemble Parts, Define Sections. | 10am | 6pm | 8
| 7/27/2015 | Assign Beam Sections. | 10am | 6pm | 8
| 7/28/2015 | Finish Beam Sections. | 10am | 6pm | 8
| 7/29/2015 | Assign Beam Orientation and Assign Column | 10am | 6pm | 8
| 7/30/2015 | Finish Column Sections. Define Connections | 10am | 6pm | 8
| 7/31/2015 | Define Dead Load. Compared Results with SAP2000 | 10am | 6pm | 8
| 8/1/2015 | Refine Connections, Assign Load, Project Meeting | 10am | 2pm | 4
| 8/3/2015 | Calculate Stiffness S12-13 | 10am | 6pm | 8
| 8/4/2015 | Make PPT for S12-13 | 10am | 6pm | 8
| 8/5/2015 | Modify PPT for S12-13, Calculate Rotation Stiffness | 10am | 6pm | 8
| 8/6/2015 | Transfer Recording Data, Calculate Rotation Stiffness | 10am | 6pm | 8
(6) Research on WTC 7 S12 - 13 Semi-rigid Condition (ABAQUS) | 8/7/2015 | Study Beam, Column Connecter. Study Assemble Method. | 10am | 6pm | 8
| 8/10/2015 | Testing Beam, Column Connecter. Transfer Recording Data. | 10am | 6pm | 8
| 8/11/2015 | Study Beam, Girder Connecter. Assemble Method. | 10am | 6pm | 8
| 8/12/2015 | Online Study Assemble Method, Test Assemble Method. | 10am | 6pm | 8
| 8/13/2015 | Divided S12-13 into 3 main parts (Deck, Beam, and Column). Divided Beam into 4 parts in order to define Semi-rigid Connections. | 10am | 6pm | 8
| 8/14/2015 | Build up New S12-13 Abaqus Model | 10am | 6pm | 8
| 8/15/2015 | Compare X-direction Stiffness between New Model and Old Model | 10am | 6pm | 8
| 8/16/2015 | Released the End Moment in the New Model. Compared Moment released condition with rigid condition | 10am | 6pm | 8
| 8/17/2015 | Calculated X-direction and Y-direction stiffness and make PPT | 10am | 6pm | 8
| 8/18/2015 | Check New S12-13 Abaqus Model in Rigid Condition, Compared with the moment released condition | 10am | 6pm | 8
| 8/19/2015 | Study Connections between Deck and Beam. Included Section (4) in PPT. | 10am | 6pm | 8
| 8/20/2015 | Included Section (2) and (3) in PPT. | 10am | 6pm | 8
(7) Strucutral Analysis of S12 - 13 (ABAQUS) | 8/26-28/2015 | Meeting, Set up Research Plan | 2pm | 6pm | 4
| 8/31-9/4/2015 | Remove Column 97, Set up Loading Condition, Apply Load on Column 97 | 2pm | 6pm | 4
| 9/7-9/11/2015 | Study Fire for WTC 7 Building, Heated 1/4 at Previous Model | 2pm | 6pm | 4
| 9/14-9/18/2015 | Make Presentation for WTC 7 | 2pm | 6pm | 4
| 9/21-9/25/2015 | WTC 7 Research Presentation | 2pm | 6pm | 4
| 9/28-10/2/2015 | Writing WTC 7 Report | 2pm | 6pm | 4